## Sheet1
FRONTEND TEAM
Date
| Mekala Sunanth |  | Maram Sandhya&Nagaveni HK |  | Mohammed Owais&Mashti Nagaraju
2022-03-25 | Day 1 | Work On Home Page | Day 1 | Work On View Order Page | Day 1 | Work On Adminlogin Services
2022-03-26 | Day 2 | Work On AdminLogin, User Login, Signup Pages | Day 2 | Work On Available Products | Day 2 | Work On User Login Registration Services
2022-03-27 | Day 3 | Work On Admin Page, User Page, Manage Products | Day 3 | Work On Gathering Components and Modification Of available Products | Day 3 | Work On Gathering Components
2022-03-28 | Day 4 | Work On Routing Pages | Day 4 | Work On About Us Page | Day 4 | Work On Contact Page
2022-03-29 | Day 5 | Work On Services | Day 5 | Work On Add View Order Page | Day 5 | Work On Cart Page
2022-03-30 | Day6 | work on modifications | Day6 | Work On Categories Page | Day6 | Work On Categories Page
2022-03-31 | Day7 | working on services | Day7 | Work On PPT | Day7 | Work On Services
BACKEND (TEAM-LEADER) Md Iqbal Quraishi
Date
| Md Iqbal Quraishi |  | Neha Desai&Namrata Tarade |  | Pallavi Pawar&Namratha.U
2022-03-25 | Day 1 | Work On FoodBox list,modules&package creation | Day 1 | work on admin login modules and package creation | Day 1 | work on userlogin modules and package creation
2022-03-26 | Day 2 | checking the functionalities of written code | Day 2 | checking the functionalities of written code | Day 2 | checking the functionalities of written code
2022-03-27 | Day 3 | work on user registration modules creation&checking the functionality | Day 3 | removing bug | Day 3 | removing bug
2022-03-28 | Day 4 | remove bug and test modules | Day 4 | work on cart module creation | Day 4 | work on database
2022-03-29 | Day 5 | Work On creating order list | Day 5 | testing cart module | Day 5 | work on database
2022-03-30 | Day 6 | Work On Cart and Order Testcases | Day 6 | Work On Admin and User Login Pages | Day 6 | Work On User SignUp Pages
2022-03-31 | Day 7 | Work On Integration | Day 7 | Work On PPT | Day 7 | Work On PPT